Memo

The selection of the immersed tunnel as the preferred solution

Introduction

An immersed tunnel is the best technical solution for a Fixed Link across the Fehmarnbelt. This conclusion is reached on technical, safety, environmental and financial grounds.

From a plan approval perspective, each of the technical solutions investigated – an immersed tunnel, a bored tunnel and a bridge – can be approved in both Germany and Denmark. Femern A/S’ extensive environmental investigations have shown that while all technical solutions would have impacts on the environment – some temporary, others longer lasting – none of them has such strong environmental consequences that they would prevent the respective solutions from being approved.

During the technical investigations, Femern A/S compared the immersed tunnel with the cable-stayed bridge, as well as the immersed tunnel with the bored tunnel. The conclusions are set out below.

Immersed tunnel vs. cable-stayed bridge

- The technical challenges of the cable-stayed bridge are greater than those of the immersed tunnel. The cable-stayed bridge would be the world’s longest of its kind with two record spans of 724 m each. While the immersed tunnel will also be the longest of its kind, the technical challenge is much less significant. Therefore, the construction risks to the cable-stayed bridge are higher.

- The cable-stayed bridge would constitute a permanent risk for shipping safety. While this risk could be minimised through the introduction of a permanent VTS-system, an element of risk would always remain and a ship collision with the potential spill of hazardous substances could have severe consequences for the environment.

- The cable-stayed bridge would expose traffic to wind and weather conditions, which could restrict the traffic flow – just as is sometimes the case on the Fehmarnsund bridge.

- The cable-stayed bridge would have a permanent impact on the marine environment since its pillars could affect the water exchange in the Fehmarnbelt.

- The cable-stayed bridge would risk causing permanent impairment to bird migration in the region.

- In terms of construction period, construction costs and maintenance costs, the immersed tunnel and the cable-stayed bridge are comparable. It would take 6 years to build the cable-stayed bridge and 6 ½ years to build the immersed tunnel. The cable-stayed bridge would be slightly more expensive during the construction phase, but a little less so during the operation and maintenance phase.

Immersed tunnel vs. bored tunnel

- The construction risk of the bored tunnel is substantially higher than for an immersed tunnel. The geological conditions in the Fehmarnbelt make it difficult to drill and to stabilise a tunnel underneath the seabed, which would need to run much deeper than the immersed tunnel.

- Moreover, to give the tunnel tubes the same functionality as the immersed tunnel, it would be necessary to build three separate tubes using six of the world’s largest tunnel boring machines – two for each tube. Four of the boring machines would need to have a diameter exceeding 15 m and two of them exceeding 16 m. Each machine would have to drill approximately 10 km through difficult and mixed ground without a major breakdown as they could not be replaced once drilling had begun.

- The bored tunnel would require a larger construction site on Fehmarn than the immersed tunnel.

- In terms of construction period (8 years), construction costs (EUR 6.8 billion) and maintenance costs, the bored tunnel is significantly more expensive – approximately EUR 1.3 billion or 25% more during construction, and 20% more during operation and maintenance. It would also take 18 months longer to build. This would lead to a considerably longer repayment period and higher interest burden, which would effectively render the project uneconomical.

Conclusion – the reasons in favour of the immersed tunnel

The overall comparison of the immersed tunnel with the other technical alternatives highlights the advantages of the immersed tunnel. The immersed tunnel is the best solution because:

- The existing technical knowledge and robustness of the construction methods is the highest among the solutions.

- There is no potential collision risk for shipping during its operation, because it runs underneath the seabed. Furthermore, it will not affect the water exchange across the Baltic Sea.

- It constitutes a safe and comfortable solution for traffic, offering escape routes every 100 metres along all four tunnel tubes. Use of the tunnel will constitute a higher safety level for road as well as for rail compared to the safety level in the open land

- Its main environmental effects are confined to the construction period, which means that it has little long-lasting or permanent effect on the environment and that no severe environmental detrimental effects can be expected